## Report
Test Case Report
Project Name | dailyfinance.roadtocareer.net
Module Name | Homepage, SignUp, SignIn, Add Cost & Edit Cost
Test Case Version | Ver_1.0
Written By | Akash Das
Executed By | Akash Das
Reviewed By | Salman Rahman
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total Test Case
| 96 | 18 | 0 | 0 | 114
Grand Total | 96 | 18 | 0 | 0 | 114
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No

## TestCaseReport
Project Name: | dailyfinance.roadtocareer.net |  |  |  | TEST CASE
Created By: | Akash Das |  |  |  | PASS | 96
Executed By: | Akash Das |  |  |  | FAIL | 18
Reviewed By: | Salman Rahman |  |  |  | Not Executed | 0
Execution Start Date: |  |  |  |  | Total | 114
Execution End Date:
Test case id | Module | Type of Testing | Features | Test Case Description | Pre-Condition | Test Step | Test Data | Expected result | Actual Result | Status | Remarks
TC001 | Homepage | UI Testing | Homepage UI | Checking spelling or grammatical mistakes | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | No spelling or grammatical mistakes | Found as per expectation | Pass
TC002 |  |  |  | Verifying the font, text color and style | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC003 |  |  |  | The Logo should be at the top of the page | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC004 |  |  |  | A login Form should be in the middle of the page | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC005 |  |  |  | Verifying mandatory field is marked with a asterisk sign | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | asterisk sign should be present | Found as per expectation | Pass
TC006 |  |  |  | Checking by hovering over the fields | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Input fields border color should be highligted | highlighted as per expectation | Pass
TC007 |  |  |  | Checking alignment of the fields | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Proper alignment of the fields should be present | Found as per expectation | Pass
TC008 |  |  |  | Password reset link should be in the login Form | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC009 |  |  |  | Registration link should be in the login Form | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC010 |  |  |  | Full page should be responsive for all types of devices | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should behave responsive for all devices | Do not behave responsive for smaller devices with viewport width below (440px ) | Fail
TC011 |  | Functional Testing |  | Password reset link should be active | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC012 |  |  |  | Registration link should be active | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC013 |  |  |  | login button should be disable | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC014 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | No spelling or grammatical mistakes | Found as per expectation | Pass
TC015 |  |  |  | Verifying the font, text color and style | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should be as per the requirement | Found as per expectation | Pass
TC016 |  |  |  | Verifying mandatory field is marked with a asterisk sign | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | asterisk sign should be present | Found as per expectation | Pass
TC017 |  |  |  | Checking alignment of the fields | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Proper alignment of the fields should be present | Found as per expectation | Pass
TC018 |  |  |  | Checking by hovering over the fields | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Input fields border color should be highligted | highlighted as per expectation | Pass
TC019 |  |  |  | All input fields with placeholder name | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | All input fields should have placeholder name | Found as per expectation | Pass
TC020 |  |  |  | Full page should be responsive for all types of devices | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should behave responsive for all devices | Found as per expectation | Pass
TC021 |  |  |  | Checking radio button for Gender is not enabled by default | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | radio button for Gender should not be enabled by default | Found as per expectation | Pass
TC022 |  |  |  | Checking 'I accept the terms and conditions' checkbox is not enabled by default | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | I accept the terms and conditions' checkbox should not be enabled by default | Found as per expectation | Pass
TC023 |  | Functional Testing |  | Keeping mandatory fields blank | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should be as per the requirement | Found as per expectation | Pass
TC024 |  |  |  | Checking firstname and lastname field is case insensitive | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input AAbbBccCC and zzZxyYY in firstname and lastname field | First Name: "AAbbBccCC" Last Name: "zzZxyYY" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should accept the provided input | Found as per expectation | Pass
TC025 |  |  |  | Entering blank at first position in firstname and lastname field | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input " AAbbBccCC" and " zzZxyYY" in firstname and lastname field | First Name: " AAbbBccCC" Last Name: " zzZxyYY" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with Entering blank at first position in firstname and lastname field | Fail
TC026 |  |  |  | Entering blank at last position of firstname and lastname field | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "AAbbBccCC " and "zzZxyYY " in firstname and lastname field 4. input all other fields with correct value and click on Register button | First Name: "AAbbBccCC " Last Name: "zzZxyYY " Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with Entering blank at last position in firstname and lastname field | Fail
TC027 |  |  |  | Checking alert message for all mandatory fields | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Keeping blank in each mandatory field and checking repeatedly by clicking on registration button | N/A | Should not let sign up without mandatory fields value. Should pop an error message | Found as per expectation | Pass
TC028 |  |  |  | Inputing firstname and lastname with special characters | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "~!@#$$%^~" and "^&&$$^" in firstname and lastname field 4. input all other fields with correct value and click on Register button | First Name: "~!@#$$%^~" Last Name: "^&&$$^" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with spacial characters as firstname and lastname | Fail
TC029 |  |  |  | Inputing firstname and lastname with numbers | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "123456" and "789456" in firstname and lastname field 4. input all other fields with correct value and click on Register button | First Name: "123456" Last Name: "798456" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with inputing numbers as firstname and lastname | Fail
TC030 |  |  |  | Inputing firstname and lastname with alphabets | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "Akash" and "Das" in firstname and lastname field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should accept the provided input | Sign up successful | Pass
TC031 |  |  |  | Entering space between alphabets for firstname and lastname | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "ak ash" and "da s" in firstname and lastname field 4. input all other fields with correct value and click on Register button | First Name: "ak ash" Last Name: "da s" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with space between alphabets for firstname and lastname | Fail
TC032 |  |  |  | Validating an email id can only be used one time | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "testofWizard@gmail.com" in email field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not allow user to register and display a pop message | Found as per expectation with an error message | Pass
TC033 |  |  |  | Checking by inputing invalid email format | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "testofWizardgmail.com" in email field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizardgmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not allow user to register and display a pop message | Found as per expectation with an error message | Pass
TC034 |  |  |  | Checking by inputing valid email format | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "testofWizard@gmail.com" in email field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should accept the provided input | Sign up successful | Pass
TC035 |  |  |  | Inputing very weak password of length one | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "5" in password field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "5" Phone Number: "01873195755" Address: "dhaka" | Should not accept the provided input | Sign up successful with one length of password | Fail
TC036 |  |  |  | Inputing very strong password of length 16 | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "1234567890234569" in password field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "1234567890234569" Phone Number: "01873195755" Address: "dhaka" | Should accept the provided input | Should accept the provided input | Pass
TC037 |  |  |  | Inputing password with special characters | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. Input "~!@#$%^&*()" in password field 4. input all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "~!@#$%^&*()" Phone Number: "018731957ab" Address: "dhaka" | Should accept the provided input | Should accept the provided input | Pass
TC038 |  |  |  | signing up without Gender radio button selection | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. input all other fields with correct value excpet Gender radio button selection and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not let sign up without gender radio button selection. Should pop an error message | Found as per expectation | Pass
TC039 |  |  |  | signing up without "I accept the terms and conditions" checkbox clicking | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. input all other fields with correct value excpet "I accept the terms and conditions" checkbox clicking and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should not let sign up without "I accept the terms and conditions" checkbox clicking. Should pop an error message | Found as per expectation | Pass
TC040 |  |  |  | inputing Invalid phone number in phone number input | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. input "12345678ab" in phone number input with all other fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "018731957ab" Address: "dhaka" | Should not accept the provided input | Sign up successful | Fail
TC041 |  |  |  | Inputing valid data for all inputs | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. input all fields with correct value and click on Register button | First Name: "akash" Last Name: "das" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" Address: "dhaka" | Should allow user to register | Sign up successful | Pass
TC042 |  |  |  | Inputing valid data for only mandatory inputs | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" 3. input all mandatory fields with correct value and click on Register button | First Name: "akash" Email: "testsofWizard@gmail.com" Password: "wizard123" Phone Number: "01873195755" | Should allow user to register | Sign up successful | Pass
TC043 |  | Usability Testing |  | Checking copy paste functionality in every field | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should copy and paste text from fields | Functioning successfully | Pass
TC044 |  |  |  | Checking keyboard tab button functionality | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should switch to another field and highlight input border | Functioning successfully | Pass
TC045 |  |  |  | Checking keyboard enter button functionality | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. look for "Don't have an account?" and click the link at "Register" | N/A | Should switch to another field | Functioning successfully | Pass
TC046 |  | UI Testing | Sign In | Checking spelling or grammatical mistakes | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | No spelling or grammatical mistakes | Found as per expectation | Pass
TC047 |  |  |  | Verifying the font, text color and style | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should be as per the requirement | Found as per expectation | Pass
TC048 |  |  |  | Verifying mandatory field is marked with an asterisk sign | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | asterisk sign should be present | Found as per expectation | Pass
TC049 |  |  |  | Checking alignment of the fields | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Proper alignment of the fields should be present | Found as per expectation | Pass
TC050 |  |  |  | Checking by hovering over the fields | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Input fields border color should be highligted | highlighted as per expectation | Pass
TC051 |  |  |  | All input fields with placeholder name | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | All input fields should have placeholder name | Found as per expectation | Pass
TC052 |  |  |  | Full page should be responsive for all types of devices | 1. Homepage should be Active 2. Register link should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should behave responsive for all devices | Found as per expectation | Pass
TC053 |  | Functional Testing |  | Keeping email and password field blank | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | N/A | Should not allow user to login and display an error messeage | Found as per expectation | Pass
TC054 |  |  |  | Checking login wrong credentials in email field | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | Email: "testsofWizards@gmail.com" password: "wizard123" | Should not allow user to login and display an error messeage | Found as per expectation | Pass
TC055 |  |  |  | Checking login wrong credentials in password field | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | Email: "testsofWizard@gmail.com" password: "wizard456" | Should not allow user to login and display an error messeage | Found as per expectation | Pass
TC056 |  |  |  | Checking login wrong credentials in email and password field | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | Email: "testsofWizards@gmail.com" password: "wizard456" | Should not allow user to login and display an error messeage | Found as per expectation | Pass
TC057 |  |  |  | Checking if the data in password is masked | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | password: "wizard123" | Should be masked | Found as per expectation | Pass
TC058 |  |  |  | Checking login with valid credentials in email and password field | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | Email: "testsofWizard@gmail.com" password: "wizard123" | Should allow user to login | Found as per expectation | Pass
TC059 |  |  |  | Verifying ‘Password reset’ functionality | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. Click on "reset it here" link | N/A | Should sent an email for recovering password | Found as per expectation | Pass
TC060 |  |  |  | Verifying change the password link is sent to valid email address | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. Click on "reset it here" link 3. Check the valid Email inbox | N/A | Should be sent to valid email address | Found as per expectation | Pass
TC061 |  |  |  | Verifying the functionality of 'Set a New Password' | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. Click on "reset it here" link | N/A | Should provide a new input for setting new password | Found as per expectation | Pass
TC062 |  |  |  | Verifying inputing old password on 'Set a New Password' | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. Click on "reset it here" link | New password: "wizard123" confirm password: "wizard123" | Should not allow user to login and display an error message | password got reset with old password | Fail
TC063 |  |  |  | Verifying inputing new password on 'Set a New Password' | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ 2. Click on "reset it here" link | New password: "wizard0123" confirm password: "wizard0123" | Should allow user to change the password | Found as per expectation | Pass
TC064 |  |  |  | Verifying login with the newly changed password | Homepage should be Active | 1. Go to https://dailyfinance.roadtocareer.net/ | Email: "testsofWizard@gmail.com" password: "wizard0123" | Should allow user to login | Found as per expectation | Pass
TC065 |  |  |  | Checking if the link gets dissolved setting a new password | N/A | 1. Check the respective Email and click on the link again | N/A | Link should get dissolved | Link is still active | Fail
TC066 | Dashboard | UI Testing | Add Cost | Checking spelling or grammatical mistakes | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | No spelling or grammatical mistakes | Found as per expectation | Pass
TC067 |  |  |  | Verifying the font, text color and style | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Should be as per the requirement | Found as per expectation | Pass
TC068 |  |  |  | Verifying mandatory field is marked with an asterisk sign | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | asterisk sign should be present | Not found as per expectation | Fail
TC069 |  |  |  | Checking alignment of the fields | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Proper alignment of the fields should be present | Found as per expectation | Pass
TC070 |  |  |  | Checking by hovering over the fields | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Input fields border color should be highligted | Not highlighted as per expectation | Fail
TC071 |  |  |  | All input fields have lebel | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | All input fields have to associated with lebel | Found as per expectation | Pass
TC072 |  |  |  | Full page should be responsive for all types of devices | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Should behave responsive for all devices | Do not behave responsive for smaller devices with viewport width below 560px | Fail
TC073 |  | Functional Testing |  | Keeping all input field blank | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Should not let add a cost and display an error messeage | Found as per expectation | Pass
TC074 |  |  |  | inputing numerical value in Item Name input | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "1" Quantity: "1" Amount: "100" Purchase Date: "10/25/2024" Month: "October" Remarks: " " | Should not let add a cost and display an error messeage | Item cost added | Fail
TC075 |  |  |  | inputing alphabet in Item Name input | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "1" Amount: "100" Purchase Date: "10/25/2024" Month: "October" Remarks: " " | Should let add a cost and display an error messeage | Found as per expectation | Pass
TC076 |  |  |  | Decremental button should be disable in quantity input | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Decremental button should be disable in quantity input when quantity is 1 | Found as per expectation | Pass
TC077 |  |  |  | Decremental button should be enable in quantity input | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Decremental button should be enable in quantity input when quantity is greater then 1 | Found as per expectation | Pass
TC078 |  |  |  | inputing alphabet into amount input field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Should not let inputting any alphabet in amount field | Found as per expectation | Pass
TC079 |  |  |  | Inputing numerical value in amount field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Amount field should take numerical value | Found as per expectation | Pass
TC080 |  |  |  | numerical negative value in amount field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | amount field should not let put numerical negative value | Can put numerical negative value | Fail
TC081 |  |  |  | numerical "0" value in amount field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "1" Amount: "0" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother " | Should not let add a cost and display an error messeage | Item cost added | Fail
TC082 |  |  |  | Keeping amount input field blank | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "1" Amount: " " Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother" | Should not let add a cost and display an error messeage | Found as per expectation | Pass
TC083 |  |  |  | Date picker functionality in Purchase Date field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Date picker in Purchase Date field should let change date | Found as per expectation | Pass
TC084 |  |  |  | Date picker functionality in Purchase Date field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Date picker in Purchase Date field should let clear out date | Found as per expectation | Pass
TC085 |  |  |  | Date picker functionality in Purchase Date field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Date picker should format the date in "MM/DD/YYYY" | Found as per expectation | Pass
TC086 |  |  |  | Date picker functionality in Purchase Date field | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | date picker Should have today's value by default | Found as per expectation | Pass
TC087 |  |  |  | Month field functionality | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | Month field should let change the month | Found as per expectation | Pass
TC088 |  |  |  | Month field functionality | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | N/A | date picker Should have current month value by default | Found as per expectation | Pass
TC089 |  |  |  | Inputing valid data for all mandatory inputs only | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "1" Amount: "20" Purchase Date: "10/25/2024" Month: "October" | Should let add a cost | Item cost added | Pass
TC090 |  |  |  | Inputing valid data for all inputs | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "1" Amount: "20" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother " | Should let add a cost | Item cost added | Pass
TC091 |  |  |  | Reset button resets input value | 1. Homepage should be Active 2. User have to be logged in | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click the "Add Cost" button | Item Name: "apple" Quantity: "2" Amount: "50" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother " | Reset button should reset all input value except those who have default value | Found as per expectation | Pass
TC092 |  | UI Testing | Edit Cost | Checking spelling or grammatical mistakes | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | No spelling or grammatical mistakes | Found as per expectation | Pass
TC093 |  |  |  | Verifying the font, text color and style | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Should be as per the requirement | Found as per expectation | Pass
TC094 |  |  |  | Checking alignment of the fields | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Proper alignment of the fields should be present | Found as per expectation | Pass
TC095 |  |  |  | Edit button color | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Edit button color should be Green or Blue | Found as per expectation | Pass
TC096 |  |  |  | Delete button color | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Edit button color should be Red | Found as per expectation | Pass
TC097 |  |  |  | Full page should be responsive for all types of devices | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Should behave responsive for all devices | Do not behave responsive for smaller devices with viewport width below 670px | Pass
TC098 |  | Functional Testing |  | All input field should be disable | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | All input field should be disable before clicking "Edit" button | Found as per expectation | Pass
TC099 |  |  |  | Back button should be active | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Back button should redirect to previous page | Found as per expectation | Pass
TC100 |  |  |  | Edit button should be active | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list | N/A | Edit button should be active and clicking on it it should active all input fields | Found as per expectation | Pass
TC101 |  |  |  | Edit button should change its text from "Edit" to "Update" | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | After clicking on Edit button, it should change its text from "Edit" to "Update" | Found as per expectation | Pass
TC102 |  |  |  | Previous input values in input fields | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | Previous input value should be there in all input fields | Found as per expectation | Pass
TC103 |  |  |  | Previous Input value can be earesed or changed | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | Previous Input value in all input fields can be earesed or changed | Found as per expectation | Pass
TC104 |  |  |  | Keeping all input field blank | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | Should not let update cost and display an error messeage | Found as per expectation | Pass
TC105 |  |  |  | Increment button on quantity selection | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | Increment button on quantity selection should be active and increment quantity by 1 after clicking | Found as per expectation | Pass
TC106 |  |  |  | Decrement button on quantity selection | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | N/A | Decrement button on quantity selection should be active and decrement quantity by 1 after clicking | Found as per expectation | Pass
TC107 |  |  |  | Keeping amount input field blank | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | Item Name: "apple" Quantity: "2" Amount: "" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother " | Should not let update cost and display an error messeage | Found as per expectation | Pass
TC108 |  |  |  | numerical "0" value in amount field | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | Item Name: "apple" Quantity: "2" Amount: "0" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother " | Should not let update cost and display an error messeage | Item cost updated | Fail
TC109 |  |  |  | Keepng Remarks field blank | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | Item Name: "apple" Quantity: "2" Amount: "50" Purchase Date: "10/25/2024" Month: "October" Remarks: "" | Should let update the item costing | Item cost updated | Pass
TC110 |  |  |  | Inputing valid data for all inputs | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button | Item Name: "apple" Quantity: "2" Amount: "20" Purchase Date: "10/25/2024" Month: "October" Remarks: "This is for my brother" | Should let update the item costing | Item cost updated | Pass
TC111 |  |  |  | After updating the cost page should be redirected to dashboard | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Edit" button 5. Update a cost with vaild data | N/A | After updating the cost, page should be redirected to dashboard | still stays at editing page | Fail
TC112 |  |  |  | Delete button should be active | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Delete" button | N/A | Clicking on Delete button should delete the item | Found as per expectation | Pass
TC113 |  |  |  | A confirmation/warning alert or massage should be displayed | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Delete" button | N/A | Clicking delete button a confirmation/warning alert or massage should be displayed | Found as per expectation | Pass
TC114 |  |  |  | Redirected to dashboard after deleting | 1. Homepage should be Active 2. User have to be logged in 3. At least one item cost have to be in the cost tracking table list | 1. Go to https://dailyfinance.roadtocareer.net/ 2. login with valid credentials 3. click on the view button in cost tracking table list 4. click on "Delete" button | N/A | After deleting the cost page should be redirected to dashboard | Found as per expectation | Pass

## Test Metrics
Test Metrics
SL no. | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (114/114)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/114)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (96/114)*100 = 84.21
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (18/114)*100 = 15.78
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/114)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A